- Project Information

Project Code		KIPDM

Project Title		Training Course for Managers and Supervisors in the Public Sector

(5Ps-B7)

Project Start		February 1, 2018

Project End		June 15, 2018

Project Price		PhP 1,139,357.16

Client Organization	Public Offering

- Project Team

Project Manager		Carina Evangelista

Team Members		Zemalyn Ronda, Gloria Lim, Loretta Balanzat, Tricia Marie

Dimalaluan, Andres Largo

Supervising Fellow	Immanuel Magalit

Consultants/RPs		Immanuel Magalit, Jose Agustin Cuenco, Ruth Rosario Gerochi,					Eleonor Rochelle Cruz, Clarissa Bautista

- Project Details

Project Description	The Training Course for Managers and Supervisors in the Public Sector (5Ps) seeks to provide the foundation for developing competent supervisors and managers who are able to create and maintain a high-performance, service-oriented, and productive work place that enables employee engagement. Premised on the framework of Service Leader, the course highlights 5Ps of management and leadership: (1) Purposes; (2) Personality; (3) People; (4) Processes; and (5) Plans to help achieve quality service and results

Project Objective	Design and implement a 15-day training course for the managers and supervisors in the public sector which targets managerial and supervisory skills

Focus Area		Leadership and management competencies

Project Type		Training

Project Beneficiary	Managers and supervisors from National Line Agencies (NLAs) and

Government Owned and Controlled Corporations (GOCCs)

- Project Accomplishments

Key Activities Implemented	Pre-Implementation Phase:

- Training Course Design

- Marketing and Registration

- Preparation of project documents

- Team Mobilization

Implementation Phase

- Conduct of 15-day training course

Post-Implementation Phase

- Revision of Financial Plan and Special Order

- Encoding of Course Evaluation and Session Evaluations

Major Outputs		Training Course Design

Conduct of Training Course (15 days)

Training Certificates / List of Graduates

Project Impact		Develop leadership and management competencies of public managers and

supervisors

Lessons Learned

- There are challenges in implementing the training program outside metro manila-very high out-of-pocket costs;

- Deploying 3 members of the project team is doable but challenging;

- Low turn-out in the number of participants affected the financial outcome of the project;

- Food at the Sarrosa Hotel receives a very low rating in the evaluation;

- DAP should send more participants to the training course;

- It is ok to give discount in the training course fee for participants coming from DAP, because we are helping our own organization;

- The DAP participants learned a lot from fellow classmates who are more senior and has more experience in being a manager;

- The design and sequencing of the modules is better for this batch: Purposes, Personality, People, Processes, and Plans;

- Although the class was small, the discussions were very meaningful; the class became very close; and

- The training course received a positive feedback from the participants.

- Attachments

- Summary of Evaluation for Course and Resource Person (for training program)

- List of Training Participants

Prepared by:							Noted / Approved by:

CARINA F. EVANGELISTA     					TRYGVE A. BOLANTE

Project Manager							Vice President / Center Head

Notes:

- Project details on Section I-III can be generated thru PMIS based on PMs Inputs.

- Project Managers are required to accomplish Section IV & provide Section V to reflect results of project implementation

- Project Managers can update/adjust the pre-filled sections(I-III) based on actual data